## Tracker
Product Design Task Tracker
PMs add a row per task (columns B–I, including effort estimate in hours). Designers update columns J–M. Everything grey is automatic. Use filters rather than sorting.
| ① PM creates the task | [7 empty] | ② Designer updates progress |  |  |  | ③ Auto-calculated
Task ID | Task Assigned | Project | PM (Project Lead) | Designer | Priority | Start Date | Target End Date | Estimated Effort (Hrs) | Status | Actual End Date | Revision Rounds | Dependencies / Blockers | TAT (Working Days) | Planned (Working Days) | Variance vs Plan (Days) | Delivery Status | Speed Score | Quality Score | Task Score | Hours per Working Day

## Scorecard
Designer Scorecard
Live from the Tracker. Scores are 0–100. Speed and Quality use tasks completed in the period below; Commitment is as of today.
Period from | 2026-09-01
Period to | 2026-09-30
Total Tasks | Completed | Open | Blocked | Overdue
0 | 0 | 0 | 0 | 0
Score by designer
Designer | Tasks Completed (period) | Avg TAT (Working Days) | On-Time % | Avg Revision Rounds | Speed Score | Quality Score | Commitment Score | Overall Score | Rating | Focus Area
Pragati | 0 | - | - | - | - | - | 100 | - | - | Needs at least one completed task in the period
Swathi | 0 | - | - | - | - | - | 100 | - | - | Needs at least one completed task in the period
Tasks by PM
PM | Tasks Created | Open | Blocked | Overdue | Avg Revision Rounds (completed)
Raghav | 0 | 0 | 0 | 0 | -
SL | 0 | 0 | 0 | 0 | -
Arun | 0 | 0 | 0 | 0 | -
Naveen | 0 | 0 | 0 | 0 | -
Manu | 0 | 0 | 0 | 0 | -
How the score works
Speed (40%): planned working days ÷ actual working days per task, capped at 100. Finishing on or before the target date scores 100.
Quality (40%): starts at 100 and drops with each revision round; reaches 0 at 4 rounds.
Commitment (20%): share of open tasks that are not past their target date. Blocked tasks (with a blocker logged) are not counted as overdue.
Overall = weighted average. Ratings: Excellent ≥ 85, Good ≥ 70, Needs Improvement ≥ 50, otherwise At Risk.
Weights, thresholds and names can be changed on the Settings tab.
Weekly workload
Show weeks from (any date) | 2026-09-29 | Capacity 48 hrs/week (5-day week = 9.6 hrs/day). Hours are spread evenly over each task's working days between Start and Target End.
Open tasks with no effort estimate (not counted in workload): 0
Designer | Week starting (Mon) | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16
| Holidays (working days) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pragati | Leave (days) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Available (hrs) | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
| Allocated (hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Utilisation | bar: 2026-09-28 to 2026-11-16
| Headroom (hrs) | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
| Status | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised
Swathi | Leave (days) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Available (hrs) | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
| Allocated (hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Utilisation | bar: 2026-09-28 to 2026-11-16
| Headroom (hrs) | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
| Status | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised
Leave (days)
Available (hrs)
Allocated (hrs)
Utilisation
Headroom (hrs)
Status
Leave (days)
Available (hrs)
Allocated (hrs)
Utilisation
Headroom (hrs)
Status
Leave (days)
Available (hrs)
Allocated (hrs)
Utilisation
Headroom (hrs)
Status

## Settings
Settings – Lists & Scoring
Blue cells are editable. Dropdowns on the Tracker and the Scorecard read from here (Scorecard shows up to 5 designers and 5 PMs).
Designers | Project Managers | Status | Priority | Project | Project Lead (PM) | Scoring Setting | Value
Pragati | Raghav | Not Started | High | Project 1 (rename) | Raghav | Speed weight (planned vs actual working days) | 40%
Swathi | SL | In Progress | Medium | Project 2 (rename) | SL | Quality weight (fewer revision rounds) | 40%
| Arun | In Review | Low | Project 3 (rename) | Arun | Commitment weight (open tasks not overdue) | 20%
| Naveen | Blocked |  | Project 4 (rename) | Naveen | Weights total (must be 100%) | 100% | OK
| Manu | Done |  | Project 5 (rename) | Manu | Revision rounds at which Quality score = 0 | 4
[6 empty] | Rating: Excellent if score ≥ | 85
[6 empty] | Rating: Good if score ≥ | 70
[6 empty] | Rating: Needs Improvement if score ≥ | 50
Below the last threshold = At Risk
[6 empty] | Workload Setting | Value
[6 empty] | Weekly working hours | 48
[6 empty] | Working days per week (5 = Mon–Fri, 6 = Mon–Sat) | 5
[6 empty] | Hours per working day (auto) | 9.6
[6 empty] | Weekend code used in date maths (auto) | 1
[6 empty] | Overloaded if utilisation above | 100%
[6 empty] | Under-utilised if utilisation below | 70%

## Leave & Holidays
Leave & Holidays
Log every designer leave (one row per continuous leave) and every company holiday. They reduce weekly capacity on the Scorecard and are excluded from TAT working days.
Designer | From | To | Type | Note | Working Days Off | Holiday Date | Holiday