## Tracker
Product Design Task Tracker
PMs add a row per task (columns B–I, including effort estimate in hours). Designers update columns J–M. Everything grey is automatic. Use filters rather than sorting.
| ① PM creates the task | [7 empty] | ② Designer updates progress |  |  |  | ③ Auto-calculated
Task ID | Task Assigned | Project | PM (Project Lead) | Designer | Priority | Start Date | Target End Date | Estimated Effort (Hrs) | Status | Actual End Date | Revision Rounds | Dependencies / Blockers | TAT (Working Days) | Planned (Working Days) | Variance vs Plan (Days) | Delivery Status | Speed Score | Quality Score | Task Score | Hours per Working Day

## Scorecard
Designer Scorecard
Live from the Tracker. Scores are 0–100. Speed and Quality use tasks completed in the period below; Commitment is as of today.
Period from | 2026-09-01
Period to | 2026-09-30
Total Tasks | Completed | Open | Blocked | Overdue
0 | 0 | 0 | 0 | 0
Score by designer
Designer | Tasks Completed (period) | Avg TAT (Working Days) | On-Time % | Avg Revision Rounds | Speed Score | Quality Score | Commitment Score | Overall Score | Rating | Focus Area
Pragati | 0 | - | - | - | - | - | 100 | - | - | Needs at least one completed task in the period
Swathi | 0 | - | - | - | - | - | 100 | - | - | Needs at least one completed task in the period
Tasks by PM
PM | Tasks Created | Open | Blocked | Overdue | Avg Revision Rounds (completed)
Raghav | 0 | 0 | 0 | 0 | -
SL | 0 | 0 | 0 | 0 | -
Arun | 0 | 0 | 0 | 0 | -
Naveen | 0 | 0 | 0 | 0 | -
Manu | 0 | 0 | 0 | 0 | -
How the score works
Speed (40%): planned working days ÷ actual working days per task, capped at 100. Finishing on or before the target date scores 100.
Quality (40%): starts at 100 and drops with each revision round; reaches 0 at 4 rounds.
Commitment (20%): share of open tasks that are not past their target date. Blocked tasks (with a blocker logged) are not counted as overdue.
Overall = weighted average. Ratings: Excellent ≥ 85, Good ≥ 70, Needs Improvement ≥ 50, otherwise At Risk.
Weights, thresholds and names can be changed on the Settings tab.
Weekly workload
Show weeks from (any date) | 2026-09-29 | Capacity 48 hrs/week (5-day week = 9.6 hrs/day). Hours are spread evenly over each task's working days between Start and Target End.
Open tasks with no effort estimate (not counted in workload): 0
Designer | Week starting (Mon) | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16
| Holidays (working days) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pragati | Leave (days) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Available (hrs) | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
| Allocated (hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Utilisation | bar: 2026-09-28 to 2026-11-16
| Headroom (hrs) | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
| Status | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised
Swathi | Leave (days) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Available (hrs) | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
| Allocated (hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Utilisation | bar: 2026-09-28 to 2026-11-16
| Headroom (hrs) | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
| Status | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised | Under-utilised
Leave (days)
Available (hrs)
Allocated (hrs)
Utilisation
Headroom (hrs)
Status
Leave (days)
Available (hrs)
Allocated (hrs)
Utilisation
Headroom (hrs)
Status
Leave (days)
Available (hrs)
Allocated (hrs)
Utilisation
Headroom (hrs)
Status

## Settings
Settings – Lists & Scoring
Blue cells are editable. Dropdowns on the Tracker and the Scorecard read from here (Scorecard shows up to 5 designers and 5 PMs).
Designers | Project Managers | Status | Priority | Project | Project Lead (PM) | Scoring Setting | Value
Pragati | Raghav | Not Started | High | Project 1 (rename) | Raghav | Speed weight (planned vs actual working days) | 40%
Swathi | SL | In Progress | Medium | Project 2 (rename) | SL | Quality weight (fewer revision rounds) | 40%
| Arun | In Review | Low | Project 3 (rename) | Arun | Commitment weight (open tasks not overdue) | 20%
| Naveen | Blocked |  | Project 4 (rename) | Naveen | Weights total (must be 100%) | 100% | OK
| Manu | Done |  | Project 5 (rename) | Manu | Revision rounds at which Quality score = 0 | 4
[6 empty] | Rating: Excellent if score ≥ | 85
[6 empty] | Rating: Good if score ≥ | 70
[6 empty] | Rating: Needs Improvement if score ≥ | 50
Below the last threshold = At Risk
[6 empty] | Workload Setting | Value
[6 empty] | Weekly working hours | 48
[6 empty] | Working days per week (5 = Mon–Fri, 6 = Mon–Sat) | 5
[6 empty] | Hours per working day (auto) | 9.6
[6 empty] | Weekend code used in date maths (auto) | 1
[6 empty] | Overloaded if utilisation above | 100%
[6 empty] | Under-utilised if utilisation below | 70%

## Leave & Holidays
Leave & Holidays
Log every designer leave (one row per continuous leave) and every company holiday. They reduce weekly capacity on the Scorecard and are excluded from TAT working days.
Designer | From | To | Type | Note | Working Days Off | Holiday Date | Holiday

## Dashboard
Performance Dashboard
Total Tasks |  | Completed |  | Open |  | Overdue |  | Blocked |  | On-Time % (all done) | Avg Task Score | Hours Logged (period)
Data behind the charts
Designer | Completed (period) | On-Time % | Avg TAT (days) | Speed | Quality | Commitment | Overall | Rating | Hours Logged (period) | Utilisation (this week)
Delivery Status | Tasks
Done On Time
Done Late
On Track
Scheduled
Overdue
Blocked
Not Scheduled
Week starting (Mon) | [5 empty] | Team Total
Product / Master Task | Product Line | Tasks | Open | Est. Hours | Hours Logged | Avg Progress %
Project | Lead PM | Tasks | Open | Completed | Overdue | Est. Hours
Request Funnel | Subtasks
Awaiting approval
Changes requested
Approved
Rejected
4E Line | Tasks | Open | Est. Hours | Hours Logged
Evaluate
Educate
Experience
Enable
GENIE Platform
Other
Deliverables done, week of | [5 empty] | Team Total
Hours per deliverable

## Task Details
Task Details
Written by Design Task Hub on export. Row 5 here is row 5 on the Tracker. Grey columns link to the Tracker; teal columns come from designers' daily updates.
Task ID | Master Task | Subtask | Task Title | Project | Designer | Status | Delivery Status | Est. Hours | Progress % | Hours Logged | Last Update | Latest Note | Assigned By | Assigned On | Brief / Link | 4E Line | Master Task Title | Request ID | Approved On | Qty | Unit | Items Done

## Daily Log
Daily Log
One row per designer update per task per day, written by Design Task Hub on export. Hours feed the Dashboard.
Date | Task ID | Designer | Master Task | Subtask | Hours | Progress % | Status | Note | Blocker

## Task Funnel
Task Funnel
Every request PMs submitted, one row per subtask, with your decision. Approved subtasks become Tracker rows (Task ID).
Request ID | Submitted | PM | 4E Line | Product | Project | Master Task | Priority | Subtask | Detail | Designer | Start | End | Est. Hours | Status | Decided On | Owner Note | Task ID | Qty | Unit

## Deliverables
Deliverables
One row per item inside a batch task (for example each video in a set of 12), written by Design Task Hub on export.
Task ID | Designer | Product | Subtask | Batch | # | Deliverable | Status | Done On | Revisions | Link